## Slide 1: Don't throw the baby out
(With the Housing System)
John Sammons
Assistant Director: Information & Technical Services
John.sammons@isoshousing.co.uk

## Slide 2: A brief history of Isos Housing
Based in North East England
Amalgamation of
  Milecastle Housing, Castle Morpeth Housing, Enterprise 5, Nomad Housing
Joined by Cestria Community Housing
Currently 550 employee's, 17,000 properties
Large geographic area with rural challenges
Ambitious growth plans
  23,000 properties and 800 employee's April 17
  In discussions with other HA's about partnership

## Slide 3: Selecting between two systems
Capita Open Housing
  Long term Capita users but also migrated from SX3 and Simdel
  Majority of users / properties on this system
Northgate Housing
  Used by Cestria Community Housing
  Used by YHN (previous service provider to Byker Community Trust)

## Slide 4: Why not CRM or ERP?
We did try…
  Microsoft Dynamics
  Project did not deliver what we expected and we found it difficult to match a sales oriented system to our customer service environment.
We needed to move quickly
  Logical to retain skills investment in Housing System / Progress SQL
One supplier focused on Dynamics as add on other had own CRM

## Slide 5: The decision process
Develop specification document
  Independent consultant
  Interviewed key stake holders and developed key requirements
  ICT Technical requirements and integration to the stack documented
Workshops over 3-4 day period
  With 100+ staff split into voting groups by functional area
  Specification responses marked by same groups ahead of demo's
  Demo questions prepared in advance
Decision taken 13 out of 15 workgroups
  Capita Housing

## Slide 6: OT1S was born
One Team 1 System

## Slide 7: The crazy decision
Throw out the evolution
  Decided to review every process
  Full data integrity and cleanse process
  Change reference numbers to make more consistent
    Tenancy, Property, patches etc
15 years of evolution had left constraints
Felt it was time for a fresh start and re-implementation
Capita thought we were mad!

## Slide 8: Creating a project team
Needed staff who were keen to make a difference
Were not frightened to start from scratch
LEAN trained
From key areas of the business
  Housing
  Trades
  Management Information
  Both organisations represented from the start
Project Board from wider stakeholders
  No Assistant or Executive Directors, all managers & staff representatives

## Slide 9: Strong project management
Extensive experience of migrations through acquisitions
Prince 2 Qualified
OGC Programme Mgt Qualified
Excellent People Skills

## Slide 10: We have always done it that way?
Ground up needs radical thinkers
Resistance is Futile!
Hearts & Minds need winning
Politics get in the way
Get the project on your Exec agenda

## Slide 11: The 'Byker' factor
Six months into our project along comes an opportunity
Cost Sharing ICT services for BCT
Migration from Northgate
October 16 deadline

## Slide 12: Lean and Leaner

## Slide 13: While you are not busy!
Desktop Infrastructure
  6 years old needs a refresh
Use VDI architecture with thin clients
Build new desktop to support more advance features of Housing System
Needs to work with both Housing Systems
Prepare for future growth

## Slide 14: What went well
Show & Tell Sessions
  External Facilitator got buy-in
  Spot the differences gave head start
Clear Business Case
Dedicated Project room
Solid Test Scripts
Extensive Training plan
  Don't underestimate this!
Bite Sized chunk training
Clear ED/AD message
  Everything is up for change

## Slide 15: What went well
Data Integrity Lead
Solid Change Control Process
Regular communications
Demo's along the way
Strong Go-Live Plan checklist
  Concise and clear about responsibilities
  Communicated clearly to business at least 3 times
Pizza, Cake, KFC, Coffee, Tea, Sweets!

## Slide 16: Marketing the Aardvark
Used the Aardvark as the face of the project
Gave away Aardvark toys, mugs, pens, mouse mats
OT1S is the new name for the Capita system
  Made clear to all staff we are doing something new
The OT1S character will be used in future internal marketing of enhancements and new features

## Slide 17: You can never communicate enough
Posters
Briefings
Demo Sessions
Road Shows
Intranet

## Slide 18: What tripped us up
Our Project Management System was not easily accessible by external partners
  Now use O365 based solution
Timescales for product selection were long and drawn out due to tender process
Ran out of test/train/reconciliation environments
Minimal User Acceptance Testing due to Byker implementation
Final training was rushed to meet timescales
  Impacted on go-live support
Key staff were single points of competence and therefore a risk

## Slide 19: What tripped us up
Underestimated the amount of technical support required
Transferred large volume of incomplete jobs under pressure from DLO
  Delayed go-live and resulted in 2 months of mop up
Data load was slow as Technical work not completed
  Change of network card driver next day gave 20 fold performance improvement!
Technical work still being completed during go-live week
Too much change in too tight a window
Finance system was a pain and support not so good
Go-Live just before Christmas impacted on post go-live support

## Slide 20: SharePoint
Working with Capita we have developed a 360 degree SharePoint Document Interface
Any document created by Open Housing HAS to be saved to SharePoint
Automatically tagged and Info Mgt Policy applied
Docs can be scanned and tagged by Barcodes
On Disposal Capita link removed automatically

## Slide 21: Designed for Office 365
Our Document Management solution is designed for O365 from the ground up
Documents can be added by Capita or directly into a SharePoint document library
Build to leverage the power of mobile solutions with O365 security

## Slide 22: Built for GDPR
Compliance
Information Management Policies
Digital Rights Management
eDiscovery
Foundation for all files to be stored, managed and disposed of

## Slide 23: Key Benefits of retaining the Housing System
We retained existing skills and knowledge
  Did find out how little some of our staff knew!
Starting from a position of understanding
  We clearly knew which bits worked and what didn't
  Staff could concentrate of function as they understood the basics
Every lean session started with demo from Capita of what was possible
  Most staff were surprised at what they 'could' do
Faster project kick off and migration due to existing knowledge

## Slide 24: Let's do it all again!
April 3rd 2017 we Amalgamate with Derwentside Homes …..